LICEUL DE ARTE „BĂLAŞA DOAMNA”TÂRGOVIŞTE

Strategic Partnership between schools, KA2 Action, Erasmus+ Programme

The Virtual Universe We Want

Implementation plan

| Activity | Target | Period of time | Evaluation indicators | Responsible |
| --- | --- | --- | --- | --- |
| Sending all the data about the project to all partners | All partners | 1.08-1.09.2016 | E-mails to all partners | Mihaela Nicolae |
| Facebook page of the project | All partners | 15.08-30.08.2016 | The number of the accesings | Carmen Antonescu |
| Disseminating information in school about the National Agency Project Approval | All the schools’ teachers, the principal of the school | 1.08-1.09.2016 | E-mail from the project coordonator | Mihaela Nicolae |
| Distributing the tasks to all partners and setting the deadlines | All partners | 1.08-1.09.2016 | E-mails to all partners | Mihaela Nicolae |
| Fill in, on the European Comission Platform all the data about the project | European Comission | 15.08.2016-20.08.2016 | ECAS - the European Comission Platform | Mihaela Nicolae |
| Meeting in school, with the management project team, to distribute the tasks and set the deadlines | The management project team | 1.09-15.09.2016 | Report of the meeting | Mihaela Nicolae |
| Making the materials for the school’s website | Teachers, students, parents, community | 1.09-15.09.2016 | The school’s website http://www.liceuldeartebalasadoamna.ro/ | Mihaela Nicolae |
| Creating the methodology for the implementation team contest for teachers | All the teachers | 1.09-15.09.2016 | The methodology | Mihaela Nicolae |
| Creating the methodology for the implementation team contest for students | All the students | 1.09-15.09.2016 | The methodology | Mihaela Nicolae |
| Organising the contest for teachers | All the teachers | 15.09-30.09.2016 | The report about the contest | Mihaela Nicolae |
| Organising the contest for students | All the students | 15.09-30.09.2016 | The report about the contest | Mihaela Nicolae |
| Creating an Erasmus+ Corner in school | All the teachers, all the students, parents, community | 30.09-15.10.2016 | Pictures of the Erasmus+ corner | Mihaela Nicolae |
| Translating from English in Romanian the questionnaire about the Internet safe navigation, from the Lithuanian team | All the students | 1.10- 09.10.2016 | The questionnaire | Andreea Dumitru |
| Distributing the questionnaire to the students | All the students | 10.10.2016 | All the questionnaires | Denisa Toader Nicoleta Păunaș Carmen Antonescu Monica Cobianu |
| Interpreting the results of the questionnaire | All the students | 14-18.10.2016 | The interpretation of the questionnaire | Carmen Antonescu |
| Creating the project’s website | All partners | 1.10- 25.10.2016 | http://thevirtualuniversewewant. weebly.com/final-products.html | Vasile Gheorghița |